Digital Chronic Care Follow-up and Monitoring Program

Week 4 Task: Monitoring, Reporting, and Performance Metrics

Performance Monitoring and Reporting Framework

| Prepared by | Shaghayegh Haghbin |
| --- | --- |
| Submission | Week 4 Project Task |
| Document type | Word DOC file |

Prepared as a structured framework for monitoring patient service quality, operational progress, resource use, and performance improvement in a digital healthcare program.

# Document Contents

| Section | Content Area |
| --- | --- |
| 1 | Executive Summary |
| 2 | Monitoring and Reporting Objectives |
| 3 | KPI Framework |
| 4 | KPI Definitions and Measurement Methods |
| 5 | Data Collection and Ownership Plan |
| 6 | Reporting Structure |
| 7 | Dashboard and Chart Design |
| 8 | Performance Reporting Process |
| 9 | Data Accuracy and Accountability Controls |
| 10 | Contingency and Corrective Action Plan |
| 11 | Quality Assurance Metrics |
| 12 | Roles, Governance, and Review Cadence |
| 13 | Conclusion |
| 14 | References |

# 1. Executive Summary

This document presents a monitoring and reporting framework for the Digital Chronic Care Follow-up and Monitoring Program. The framework is designed to track project progress, patient experience, service efficiency, platform performance, budget use, staff readiness, and reporting quality throughout the project lifecycle.

The plan defines key performance indicators, measurement methods, data collection responsibilities, reporting formats, dashboard elements, escalation triggers, and corrective action procedures. It supports timely decision-making, transparent communication, and consistent accountability across clinical, administrative, technology, and management teams.

The framework also supports quality assurance by defining how data will be checked, how reporting delays will be handled, and how performance issues will be escalated. By using clear metrics and scheduled reporting, the project team can identify issues early, protect service quality, and maintain alignment with project objectives.

# 2. Monitoring and Reporting Objectives

The monitoring and reporting framework is built to ensure that project performance is visible, measurable, and actionable. The objectives are listed below.

Track project progress against approved milestones and implementation activities.

Measure patient satisfaction, appointment attendance, and follow-up completion.

Monitor staff readiness, response times, and workload-related service indicators.

Evaluate platform availability, technical issue closure, and dashboard update quality.

Track budget usage and identify cost variance before it affects delivery.

Provide management with clear and timely progress reports for decision-making.

Create a structured process for corrective action when performance drops below target.

# 3. KPI Framework

The KPI framework links project goals to measurable indicators. Each KPI has a target, owner, and reporting rhythm. The indicators cover patient experience, service delivery, technical performance, budget control, and reporting quality.

| KPI Area | KPI | Target | Primary Owner | Reporting Rhythm |
| --- | --- | --- | --- | --- |
| Patient Experience | Patient satisfaction score | 4.0 out of 5 or higher | Admin Coordinator | Monthly |
| Patient Engagement | Appointment attendance rate | 85% or higher | Admin Coordinator | Weekly |
| Patient Engagement | Onboarding completion rate | 90% or higher | Admin Coordinator | Weekly |
| Care Coordination | Follow-up completion rate | 90% or higher | Healthcare Lead | Weekly |
| Service Efficiency | Average response time to patient queries | Under 24 hours | Admin Coordinator | Weekly |
| Technical Performance | Platform uptime | 95% or higher | IT Support Officer | Weekly |
| Technical Support | Technical issue closure rate | 85% closed within 24 hours | IT Support Officer | Weekly |
| Resource Use | Budget variance | Within 10% of approved budget | Project Manager | Monthly |
| Staff Readiness | Staff training completion | 100% | Training Coordinator | At milestone review |
| Reporting Quality | Reports submitted on time | 100% | Project Manager | Weekly and monthly |

# 4. KPI Definitions and Measurement Methods

The following measurement table explains how each indicator will be calculated, what data will be used, and how often it will be reviewed. The aim is to make each metric clear, repeatable, and easy to audit.

| KPI | Data Collected | Measurement Method | Review Frequency |
| --- | --- | --- | --- |
| Patient satisfaction score | Survey ratings and written comments | Average score from patient feedback forms after appointments | Monthly |
| Appointment attendance rate | Scheduled appointments and completed appointments | Completed appointments divided by scheduled appointments | Weekly |
| Onboarding completion rate | Completed consent forms, patient profiles, and guidance confirmations | Completed onboarding records divided by total invited patients | Weekly |
| Follow-up completion rate | Planned follow-ups and completed follow-ups | Completed follow-ups divided by planned follow-ups | Weekly |
| Average response time | Patient query time stamp and staff reply time stamp | Average number of hours between query receipt and first response | Weekly |
| Platform uptime | Platform availability log and downtime records | Available service hours divided by planned service hours | Weekly |
| Technical issue closure rate | Issue log, priority level, open date, closure date | Issues closed within 24 hours divided by total issues raised | Weekly |
| Budget variance | Approved budget, actual spending, committed spending | Difference between planned and actual cost as a percentage | Monthly |
| Staff training completion | Attendance records and training checklist completion | Number of trained staff divided by total assigned staff | Milestone review |
| Report submission timeliness | Report due date and report submission date | Reports submitted on or before due date divided by total reports due | Weekly and monthly |

# 5. Data Collection and Ownership Plan

Data collection will follow a structured ownership model. Each data source has an assigned owner who is responsible for accuracy checks, timely updates, and issue reporting. Data will be reviewed before being included in dashboards or management reports.

| Data Source | Information Collected | Owner | Control Check |
| --- | --- | --- | --- |
| Appointment schedule | Booking volume, completed appointments, missed appointments, rescheduled appointments | Admin Coordinator | Weekly check against attendance logs |
| Patient feedback form | Satisfaction score, ease-of-use rating, comments, concerns | Admin Coordinator | Check missing or duplicate responses |
| Patient monitoring forms | Follow-up completion, submitted updates, missing information | Healthcare Lead | Clinical review of incomplete records |
| Project dashboard | Task status, milestones, KPI trends, risk status | Project Manager | Review against project tracker |
| Issue tracker | Technical incidents, response time, closure time, recurring issues | IT Support Officer | Check open items and priority levels |
| Budget tracker | Planned spend, actual spend, committed costs, remaining budget | Project Manager | Monthly reconciliation |
| Training records | Attendance, assessment completion, SOP acknowledgement | Training Coordinator | Match attendance against staff list |

# 6. Reporting Structure

Reporting will be organized by audience and decision need. Operational teams require frequent short updates, while management requires summary reporting focused on progress, risk, budget, and decisions required.

| Report | Audience | Frequency | Format | Owner |
| --- | --- | --- | --- | --- |
| Weekly Progress Report | Project team | Weekly | Dashboard summary and action log | Project Manager |
| KPI Performance Report | Project sponsor and management | Every two weeks | Word summary with charts and RAG status | Project Manager |
| Technical Issue Report | IT team and project manager | Weekly | Issue tracker export and summary notes | IT Support Officer |
| Patient Feedback Summary | Clinical and admin teams | Monthly | Survey summary with key themes | Admin Coordinator |
| Budget Status Report | Management | Monthly | Budget table with variance notes | Project Manager |
| Training Completion Report | Healthcare lead and project manager | At training milestone | Attendance and checklist record | Training Coordinator |
| Final Performance Report | All key stakeholders | End of project | Full report with lessons learned | Project Manager |

# 7. Dashboard and Chart Design

The dashboard will provide a quick performance view using targets, current status, trend direction, and RAG status. It will support timely review of indicators that need attention.

| Metric | Target | Current Status | RAG Status | Action Required |
| --- | --- | --- | --- | --- |
| Patient satisfaction | 4.0/5 or higher | 4.3/5 | Green | Continue current approach |
| Appointment attendance | 85% or higher | 82% | Amber | Improve reminders and schedule follow-up calls |
| Onboarding completion | 90% or higher | 91% | Green | Maintain onboarding checks |
| Follow-up completion | 90% or higher | 88% | Amber | Review missed follow-up reasons |
| Technical issue closure | 85% within 24 hours | 83% | Amber | Prioritize recurring platform issues |
| Budget variance | Within 10% | 7% | Green | Continue monthly review |
| Training completion | 100% | 100% | Green | Keep records updated |

The chart below is an example of how KPI performance can be shown in a management report. The chart compares selected current results with their targets so that performance gaps are visible during review meetings.

| RAG Status | Meaning | Typical Action |
| --- | --- | --- |
| Green | Performance is on target or above target. | Continue monitoring and document good practice. |
| Amber | Performance is slightly below target or showing risk. | Assign an owner, identify cause, and review in the next report. |
| Red | Performance is below target and may affect outcomes. | Escalate, approve corrective action, and monitor until resolved. |

# 8. Performance Reporting Process

The reporting process ensures that data is collected, checked, summarized, reviewed, and acted upon in a consistent way. This process also creates an audit trail for decisions and corrective actions.

| Step | Process Activity | Responsible Role | Output |
| --- | --- | --- | --- |
| 1 | Collect data from appointment schedules, feedback forms, issue trackers, budget records, and training logs. | Assigned data owner | Updated data source |
| 2 | Check data for missing entries, duplicate records, inconsistent dates, or unusual values. | Assigned data owner | Cleaned data set |
| 3 | Update the KPI dashboard and calculate current performance against targets. | Project Manager | Updated dashboard |
| 4 | Prepare weekly or monthly report using the approved reporting template. | Project Manager | Performance report |
| 5 | Review amber and red indicators with the relevant owner. | Project Manager and owner | Issue notes and actions |
| 6 | Assign corrective actions with due dates and record them in the action log. | Project Manager | Action tracker update |
| 7 | Share the report with the correct audience and store the approved copy. | Project Manager | Distributed report |
| 8 | Review whether corrective actions improved the KPI in the next reporting cycle. | Project team | Improvement status update |

# 9. Data Accuracy and Accountability Controls

The quality of reporting depends on consistent data control. The project will use the following controls to reduce errors and improve accountability.

Use a standard naming format for reports, trackers, and weekly dashboard files.

Lock formulas in the KPI tracker to reduce accidental calculation errors.

Require each data owner to complete a weekly accuracy check before reporting.

Use one approved source for each KPI to prevent conflicting figures.

Record all corrective actions with an owner, due date, and status update.

Store reports in a controlled folder with version dates and approval notes.

Review sensitive patient-related data using privacy and access control rules.

| Control Area | Control Method | Expected Result |
| --- | --- | --- |
| Data completeness | Weekly review for missing fields and blank values | Reduced missing data |
| Data consistency | Use standard data definitions and formulas | Comparable reports across weeks |
| Access control | Limit tracker editing rights to assigned owners | Lower risk of accidental edits |
| Version control | Use dated file names and retain final approved reports | Clear audit trail |
| Decision tracking | Record management decisions and action owners | Improved accountability |

# 10. Contingency and Corrective Action Plan

Corrective action is required when performance is below target, when data quality is weak, or when risks threaten delivery. The table below defines triggers and actions.

| Performance Issue | Trigger | Corrective Action | Escalation Owner |
| --- | --- | --- | --- |
| Low patient satisfaction | Average score below 4.0/5 | Review feedback themes, simplify instructions, improve support scripts | Project Manager |
| Low appointment attendance | Attendance below 85% | Increase reminder calls, review appointment times, track repeated no-shows | Admin Coordinator |
| Low onboarding completion | Completion below 90% | Check form clarity, contact patients with incomplete onboarding, reduce unnecessary steps | Admin Coordinator |
| Slow response time | Average response time above 24 hours | Reassign workload, introduce daily query checks, update response priorities | Project Manager |
| Unresolved technical issues | Closure rate below 85% within 24 hours | Escalate high-impact issues, assign priority categories, review recurring causes | IT Lead |
| Budget overrun | Variance above 10% | Review non-essential costs, use contingency reserve, seek sponsor approval | Project Sponsor |
| Delayed reporting | Report submitted after deadline | Use fixed templates, confirm owners, prepare data one day earlier | Project Manager |
| High missing data rate | Missing data above 5% | Retrain data owners, simplify forms, run weekly completeness checks | Project Manager |

# 11. Quality Assurance Metrics

Quality assurance metrics measure the reliability of the reporting framework itself. These metrics help ensure that the project team can trust the information used for decisions.

| Quality Metric | Target | Evidence Source | Review Frequency |
| --- | --- | --- | --- |
| KPI data accuracy | 95% or higher | Spot checks and data owner confirmation | Monthly |
| Reports submitted on time | 100% | Report submission log | Weekly and monthly |
| Missing data rate | Below 5% | KPI tracker completeness check | Weekly |
| Corrective actions completed on time | 85% or higher | Action tracker | Every two weeks |
| Dashboard updated on schedule | Weekly | Dashboard version history | Weekly |
| Stakeholder satisfaction with reports | 4.0 out of 5 or higher | Short management and team survey | Monthly |
| Issue log closure documentation | 95% complete | Issue tracker audit | Monthly |

# 12. Roles, Governance, and Review Cadence

Governance clarifies who reviews results, who approves corrective action, and how often decisions are made. This structure prevents unclear ownership and supports faster problem-solving.

| Role | Monitoring Responsibility | Decision Authority |
| --- | --- | --- |
| Project Sponsor | Reviews high-level progress, major risks, and budget variance | Approves major corrective actions and budget changes |
| Project Manager | Maintains KPI dashboard, prepares reports, manages action tracker | Approves operational changes within project scope |
| Healthcare Lead | Reviews patient follow-up quality and care coordination indicators | Approves workflow improvements with clinical impact |
| Admin Coordinator | Tracks scheduling, reminders, attendance, and patient feedback | Approves day-to-day scheduling adjustments |
| IT Support Officer | Tracks platform performance and technical issue closure | Escalates technical risks to IT lead |
| Training Coordinator | Tracks training completion and SOP acknowledgement | Recommends additional training where needed |
| Data Protection Officer | Reviews privacy-sensitive reporting and access controls | Approves data handling requirements |

## Review Cadence

| Review Type | Frequency | Participants | Purpose |
| --- | --- | --- | --- |
| Weekly operations review | Weekly | Project manager, admin, healthcare lead, IT support | Review active KPIs, issues, and weekly action items |
| Management review | Every two weeks | Project sponsor, project manager, management team | Review milestone progress, budget status, risk exposure, and decisions needed |
| Monthly quality review | Monthly | Project manager, healthcare lead, data protection officer, admin coordinator | Review data quality, patient feedback, service quality, and reporting reliability |
| End-of-project review | Final week | All key stakeholders | Review outcomes, lessons learned, and improvement plan |

# 13. Conclusion

This monitoring and reporting framework provides a practical structure for measuring the performance of the Digital Chronic Care Follow-up and Monitoring Program. It defines clear KPIs, data collection methods, reporting responsibilities, dashboard design, corrective actions, and quality checks.

The framework supports timely reporting, transparent decision-making, and continuous improvement. By reviewing performance on a weekly, biweekly, and monthly basis, the project team can identify issues early, protect patient service quality, manage budget use, and keep implementation activities aligned with approved objectives.

# 14. References

World Health Organization. (2021). Global strategy on digital health 2020-2025. WHO.

American Medical Association. (2020). Telehealth Implementation Playbook. AMA Digital Health Series.

U.S. Department of Health and Human Services. (2024). Introduction to privacy and security for telehealth. Telehealth.HHS.gov.

U.S. Department of Health and Human Services. (2023). HIPAA and telehealth. HHS Office for Civil Rights.