Stakeholder Communication and Engagement Plan

Digital Chronic Care Follow-up and Monitoring Program

Week 3 Task

| Prepared by | Shaghayegh Haghbin |
| --- | --- |
| Prepared for | Project Planning and Strategy Assessment |
| Document Type | Stakeholder Communication and Engagement Plan |

Document Purpose This document defines how patients, clinical teams, IT, administration, privacy, and leadership stakeholders will receive clear updates, provide feedback, escalate issues, and stay aligned throughout the healthcare project lifecycle.

# 1. Executive Summary

This communication and engagement plan supports the Digital Chronic Care Follow-up and Monitoring Program, a healthcare initiative designed to improve continuity of care for patients with chronic conditions through digital consultations, structured patient onboarding, home-based health updates, appointment reminders, and KPI reporting.

The plan defines stakeholders, communication channels, update frequency, meeting routines, feedback loops, escalation rules, reporting standards, and quality metrics. The objective is to keep all stakeholder groups informed, accountable, and engaged while protecting patient privacy and supporting safe service delivery.

Strong communication is essential because the project depends on coordination between patients, clinical staff, administrative staff, IT support, data protection, and senior management. This plan creates a practical structure for decision-making, issue resolution, and project progress tracking.

# 2. Project Communication Objectives

The communication plan is built around six practical objectives:

Provide timely and transparent updates to all stakeholder groups.

Clarify roles, responsibilities, decision rights, and reporting expectations.

Support patient understanding of appointments, onboarding, consent, and feedback processes.

Enable fast resolution of technical, clinical, scheduling, and privacy-related issues.

Maintain reliable documentation of meetings, decisions, risks, action items, and changes.

Measure communication effectiveness and adjust the approach when gaps are identified.

# 3. Communication Principles

| Principle | Application in the Project |
| --- | --- |
| Clarity | Messages should be simple, specific, and action-oriented. Each update should explain what changed, who is responsible, and what happens next. |
| Consistency | Project updates should follow the agreed schedule so stakeholders know when to expect information. |
| Accountability | Action items must include an owner, deadline, status, and follow-up route. |
| Confidentiality | Patient information must be shared only with authorized individuals through approved channels. |
| Accessibility | Patient-facing communication should use plain language and avoid unnecessary technical wording. |
| Two-way engagement | Stakeholders should have clear routes to ask questions, share concerns, and suggest improvements. |

# 4. Stakeholder Identification and Analysis

Stakeholders were identified based on their role in service delivery, decision-making authority, technical responsibility, privacy responsibility, and level of direct interaction with patients. The table below classifies stakeholders by influence, interest, and recommended engagement level.

| Stakeholder | Role in Project | Influence | Interest | Engagement Level |
| --- | --- | --- | --- | --- |
| Patients | Use the care service, attend appointments, submit health updates, and provide feedback. | Medium | High | Keep informed and supported |
| Doctors and Nurses | Deliver digital consultations, review patient information, document care actions, and raise clinical concerns. | High | High | Manage closely |
| Project Manager | Coordinates timeline, tasks, risks, issues, reporting, and stakeholder alignment. | High | High | Manage closely |
| Healthcare Lead | Approves clinical workflow, patient journey, care documentation, and service standards. | High | High | Manage closely |
| IT Team | Configures platforms, manages access, supports users, and resolves technical issues. | High | Medium | Manage closely |
| Administration Team | Schedules appointments, sends reminders, maintains communication logs, and supports patient onboarding. | Medium | High | Engage regularly |
| Data Protection Officer | Reviews consent, privacy, access controls, and secure information handling. | High | High | Manage closely |
| Training Coordinator | Prepares training materials and ensures staff readiness before launch. | Medium | Medium | Engage regularly |
| Senior Management | Approves budget, reviews milestones, monitors risks, and makes major project decisions. | High | Medium | Keep satisfied |
| Technology Vendor | Provides product support, system guidance, and service issue assistance when required. | Medium | Medium | Monitor and engage as needed |

# 5. Stakeholder Classification Matrix

The stakeholder classification matrix helps prioritize communication effort. Stakeholders with high influence and high interest require close management because they can strongly affect the success of the project. Stakeholders with high interest and lower decision authority still require regular support, especially patients and administration staff.

| Category | Stakeholders | Communication Approach |
| --- | --- | --- |
| Manage Closely | Project Manager, Healthcare Lead, Doctors and Nurses, IT Team, Data Protection Officer | Frequent meetings, action tracking, issue reviews, risk updates, decision records |
| Keep Satisfied | Senior Management, Project Sponsor | Milestone reports, budget updates, risk summaries, decision papers |
| Keep Informed | Patients, Administration Team, Training Coordinator | Clear instructions, reminders, feedback routes, progress updates |
| Monitor | Technology Vendor and external support contacts | Issue-based communication, service tickets, milestone-specific updates |

# 6. Communication Channels

Different stakeholder groups require different communication channels. Patient messages should be clear and easy to act on. Internal messages should support coordination, accountability, and auditability. Sensitive information should only be shared through approved and secure channels.

| Channel | Purpose | Main Audience |
| --- | --- | --- |
| Email | Formal approvals, meeting summaries, reports, risk updates, and stakeholder notices. | Project team, leadership, privacy, clinical and administrative stakeholders |
| Online meeting | Progress reviews, decision discussions, workflow alignment, training sessions, and issue resolution. | Project team, clinical staff, IT, administration, management |
| Project dashboard | Task status, milestones, KPI progress, risk items, and action tracking. | Project manager, project team, management |
| Secure messaging tool | Short internal reminders, quick coordination, and urgent operational updates. | Project team, IT, administration, clinical lead |
| SMS or email reminder | Appointment reminders, onboarding instructions, preparation steps, and feedback links. | Patients |
| Feedback form | Structured feedback on patient experience, staff workflow, and technical performance. | Patients, clinical staff, administration staff |
| Issue tracker | Technical errors, access problems, workflow blockers, and escalation records. | IT, project manager, administration, clinical lead |

# 7. Communication Matrix

The communication matrix defines what information is shared, who receives it, how often it is shared, and who owns the communication. This section should be used as the main communication operating guide during implementation.

| Audience | Information Shared | Channel | Frequency | Owner |
| --- | --- | --- | --- | --- |
| Project Team | Task progress, blockers, risks, upcoming milestones, action items | Online meeting and dashboard | Weekly | Project Manager |
| Senior Management | Milestone progress, budget status, risk summary, decisions required | Email report and leadership review | Every two weeks | Project Manager |
| Doctors and Nurses | Workflow updates, patient journey changes, documentation standards, training reminders | Clinical meeting and email | Weekly during setup and pilot | Healthcare Lead |
| IT Team | Access requests, platform configuration, dashboard updates, system issues, testing results | Issue tracker and technical meeting | Twice weekly during testing | IT Lead |
| Administration Team | Scheduling rules, reminder templates, onboarding status, patient contact logs | Dashboard, email, and team check-in | Weekly | Admin Coordinator |
| Patients | Appointment instructions, consent steps, preparation notes, reminders, feedback link | SMS, email, and support call when needed | Before and during pilot | Admin Coordinator |
| Data Protection Officer | Consent forms, access controls, privacy risks, incident concerns | Email and review meeting | At key milestones and as needed | Project Manager |
| Training Coordinator | Training attendance, learning gaps, material updates, completion status | Email and training tracker | Weekly during training | Training Coordinator |
| Technology Vendor | Service tickets, setup questions, configuration issues, product support items | Support portal or email | As needed | IT Lead |

# 8. Engagement Strategy by Stakeholder Group

| Stakeholder Group | Engagement Strategy |
| --- | --- |
| Patients | Use simple language, provide step-by-step appointment instructions, send reminders, offer support for access issues, and request feedback after appointments. |
| Doctors and Nurses | Involve staff in workflow design, provide training, share updates on patient journey changes, and review feedback during weekly clinical check-ins. |
| IT Team | Maintain a visible issue tracker, schedule structured testing reviews, define response times, and document fixes before pilot launch. |
| Administration Team | Provide clear scheduling scripts, reminder templates, patient contact procedures, and escalation routes for missed appointments or access concerns. |
| Data Protection Officer | Request review of consent wording, access controls, approved communication channels, privacy risks, and any incident handling procedure. |
| Senior Management | Provide short milestone reports, highlight budget or timeline concerns early, and request decisions only when clear options and impacts are defined. |
| Technology Vendor | Use structured tickets with screenshots, issue priority, user impact, expected resolution date, and closure confirmation. |

# 9. Meeting Schedule and Protocols

Meetings should be structured, time-bound, and focused on decisions, blockers, risks, and next steps. Each meeting should produce clear notes and action items. The project manager owns the overall meeting rhythm.

| Meeting | Participants | Frequency | Main Content |
| --- | --- | --- | --- |
| Weekly Project Meeting | Project manager, IT lead, admin coordinator, healthcare lead, training coordinator | Weekly | Task progress, blockers, risks, next steps, action item status |
| Clinical Workflow Meeting | Doctors, nurses, healthcare lead, project manager | Weekly during setup and pilot | Patient journey, appointment workflow, documentation, quality concerns |
| Technical Testing Meeting | IT team, admin coordinator, project manager, vendor when needed | Twice weekly during testing | Platform access, dashboard checks, issue log, testing results |
| Management Update | Project manager, sponsor, senior management, healthcare lead | Every two weeks | Timeline, budget, milestone status, risks, decisions required |
| Pilot Review Meeting | Project team, clinical lead, IT, admin, data protection officer when required | Weekly during pilot | Patient feedback, technical issues, adoption, improvement actions |
| Privacy Review Checkpoint | Data protection officer, project manager, IT lead, admin coordinator | Before onboarding and before launch | Consent, secure communication, access controls, documentation standards |

## 9.1 Meeting Protocols

A short agenda should be sent before each scheduled meeting.

Attendance should be recorded for project governance and follow-up.

Decisions should be documented with the decision owner and date.

Action items should include an owner, due date, priority, and status.

Meeting notes should be shared within 24 hours.

Risks, issues, and changes raised in meetings should be moved into the correct log.

Patient information should not be included in general meeting notes unless there is an approved need and safe handling method.

# 10. Feedback Collection Strategy

Feedback will be collected from patients, clinical staff, administration staff, IT, and leadership. Feedback will be used to improve patient communication, staff workflow, technical support, and reporting quality.

| Feedback Source | Method | Frequency | Purpose |
| --- | --- | --- | --- |
| Patients | Short survey, support call notes, appointment experience questions | After first appointment and at pilot end | Measure ease of use, satisfaction, understanding, and support needs |
| Doctors and Nurses | Feedback form and clinical meeting discussion | Weekly during pilot | Identify workflow gaps, documentation concerns, and care coordination issues |
| Administration Team | Issue log, scheduling tracker, weekly check-in | Weekly | Improve appointment coordination, reminders, and patient contact process |
| IT Team | Technical issue tracker and testing notes | Ongoing | Track access issues, platform problems, dashboard errors, and response time |
| Senior Management | Management review feedback | Every two weeks | Confirm strategic alignment, timeline confidence, and decision needs |
| Data Protection Officer | Privacy review notes and exception log | At key milestones | Confirm that communication and documentation practices meet privacy expectations |

# 11. Escalation Protocol

The escalation process ensures that unresolved issues are addressed quickly by the right decision-maker. Issues should be logged, prioritized, assigned, and closed only after the responsible owner confirms resolution.

| Issue Type | First Level Owner | Escalation Level | Expected Response | Example Trigger |
| --- | --- | --- | --- | --- |
| Patient appointment issue | Admin Coordinator | Project Manager | Same day | Missed appointment, unclear appointment details, patient cannot access instructions |
| Technical issue | IT Support Officer | IT Lead | Within 24 hours | Login issue, dashboard error, video call failure, reminder system issue |
| Clinical workflow issue | Healthcare Lead | Project Sponsor | Within 48 hours | Unclear care handover, documentation problem, patient pathway confusion |
| Privacy or consent concern | Data Protection Officer | Senior Management | Immediate | Consent concern, unauthorized access risk, sensitive information shared incorrectly |
| Budget or timeline delay | Project Manager | Project Sponsor | Within 48 hours | Cost increase, dependency delay, resourcing shortage |
| Training readiness gap | Training Coordinator | Project Manager | Within 24 hours | Staff missed training, assessment not completed, support materials unclear |

# 12. Documentation and Reporting Plan

Documentation should create a clear audit trail for decisions, risks, communication, and change requests. All project documents should be stored in an approved shared workspace with controlled access.

| Document | Content | Owner | Timing |
| --- | --- | --- | --- |
| Meeting minutes | Meeting decisions, discussion summary, attendance, action items | Project Manager | Within 24 hours of meeting |
| Decision log | Major decisions, rationale, approver, date, impact | Project Manager | Updated when decisions are made |
| Action tracker | Task owner, due date, priority, status, dependencies | Project Manager | Updated weekly |
| Risk and issue log | Risk description, impact, owner, mitigation, status | Project Manager | Updated weekly or as needed |
| Patient feedback summary | Trends from patient surveys and support notes | Admin Coordinator | Weekly during pilot |
| Staff feedback summary | Clinical, IT, training, and admin feedback themes | Healthcare Lead and Project Manager | Weekly during pilot |
| KPI report | Communication metrics, training completion, issue response, satisfaction results | Project Manager | Every two weeks |
| Change request record | Change description, reason, impact, approval, implementation status | Project Manager | As needed |

# 13. Reporting Structure

Reporting should be practical and focused on the information each stakeholder needs. Reports should highlight progress, blockers, risks, decisions required, and next steps rather than including unnecessary detail.

| Report | Audience | Key Content |
| --- | --- | --- |
| Weekly Project Update | Project team | Progress against schedule, risks, issues, action status, upcoming tasks |
| Management Summary | Senior management and sponsor | Milestone status, budget summary, major risks, decisions needed |
| Clinical Workflow Summary | Healthcare lead, doctors, nurses | Workflow updates, patient process issues, documentation changes, training needs |
| Technical Status Report | IT lead and project manager | Testing results, open issues, access status, dashboard readiness |
| Pilot Feedback Summary | Project team and management | Patient feedback, staff feedback, appointment attendance, improvement actions |
| Privacy Checkpoint Report | Data protection officer and project manager | Consent status, access controls, approved communication channels, unresolved privacy concerns |

# 14. Communication Quality Assurance Metrics

Communication performance will be reviewed throughout implementation. If a metric falls below target, the project manager will review root causes and adjust channels, frequency, message format, or ownership.

| Metric | Target | Data Source | Review Frequency |
| --- | --- | --- | --- |
| Meeting attendance rate | 90% or higher | Attendance record | Weekly |
| Action items completed on time | 85% or higher | Action tracker | Weekly |
| Meeting notes shared on time | Within 24 hours | Meeting minutes log | Weekly |
| Management reports submitted on time | 100% | Report tracker | Every two weeks |
| Patient reminder delivery rate | 95% or higher | Reminder system log | Weekly during pilot |
| Patient feedback response rate | 70% or higher | Feedback forms | After appointment and pilot end |
| Technical issue response time | Within 24 hours | Issue tracker | Weekly |
| Stakeholder satisfaction with communication | 4 out of 5 or higher | Survey or feedback form | Pilot end |
| Escalated issues closed within target | 85% or higher | Issue and escalation log | Weekly |

# 15. Change Communication Process

Project changes may affect schedule, budget, workflow, training, patient communication, or reporting. The project will use a structured change communication process to avoid confusion and maintain stakeholder confidence.

| Step | Action |
| --- | --- |
| 1. Identify change | Record the requested change, reason, stakeholder source, and urgency. |
| 2. Assess impact | Review impact on timeline, budget, patient experience, privacy, workflow, and resources. |
| 3. Approve or reject | Obtain approval from the project sponsor or relevant decision owner for significant changes. |
| 4. Update documents | Revise the schedule, communication matrix, risk log, workflow notes, or training materials as needed. |
| 5. Communicate change | Send a clear summary explaining what changed, who is affected, and when the change starts. |
| 6. Monitor result | Check whether the change solved the issue and update the action tracker. |

# 16. Risk Considerations for Communication

| Communication Risk | Impact | Mitigation |
| --- | --- | --- |
| Stakeholders miss key updates | Medium | Use scheduled updates, meeting notes, dashboard reminders, and clear action ownership. |
| Patients misunderstand instructions | High | Use plain language, reminder messages, support calls when needed, and feedback questions. |
| Technical issues are not escalated quickly | High | Use the issue tracker, define response times, and hold testing meetings. |
| Sensitive information shared incorrectly | High | Use approved channels, access controls, privacy checks, and staff reminders. |
| Management decisions are delayed | Medium | Provide concise decision papers with options, impact, and recommended action. |
| Feedback is collected but not acted on | Medium | Review feedback weekly, assign owners, and track improvement actions. |

# 17. Implementation Timeline for Communication Activities

| Week | Communication Activity |
| --- | --- |
| Week 1 | Confirm stakeholder list, communication objectives, meeting rhythm, and reporting templates. |
| Week 2 | Approve communication matrix, escalation routes, documentation standards, and update templates. |
| Week 3 | Start weekly project meetings and clinical workflow communication. |
| Week 4 | Launch technical coordination meetings and issue tracking process. |
| Week 5 | Prepare patient communication templates, onboarding instructions, and feedback questions. |
| Week 6 | Share staff training communication and confirm attendance tracking. |
| Week 7 | Send pre-launch updates to internal stakeholders and review readiness concerns. |
| Week 8 | Test reminder messages, feedback forms, issue tracker, and reporting dashboard. |
| Week 9 | Begin pilot communication with patients and provide daily issue monitoring during launch week. |
| Week 10 | Review patient and staff feedback, identify communication gaps, and update materials. |
| Week 11 | Escalate unresolved issues and communicate workflow improvements. |
| Week 12 | Submit final communication effectiveness summary and lessons learned. |

# 18. Conclusion

This stakeholder communication and engagement plan provides a clear structure for managing communication across the Digital Chronic Care Follow-up and Monitoring Program. It identifies stakeholders, classifies their influence and interest, defines communication channels, sets meeting and reporting standards, and explains how feedback and escalations will be handled.

The plan supports transparency, accountability, privacy-conscious communication, and continuous improvement. By following the communication matrix, meeting protocols, feedback process, and quality metrics, the project team can reduce confusion, respond quickly to issues, and maintain stakeholder confidence throughout implementation.

# 19. References

World Health Organization. Global Strategy on Digital Health 2020-2025.

American Medical Association. Telehealth Implementation Playbook.

U.S. Department of Health and Human Services. Telehealth Privacy and Security Guidance.

Project Management Institute. A Guide to the Project Management Body of Knowledge, stakeholder engagement and communications management principles.