Chronic Care Follow-up and
Monitoring Program

Week 2 Task: Implementation Planning and Resource Allocation

| Prepared by | Shaghayegh Haghbin |
| --- | --- |
| Course Task | Week 2 Task: Implementation Planning and Resource Allocation |
| Project Type | Healthcare Initiative |
| Planning Horizon | 12-week implementation roadmap |

# 1. Executive Summary

This document presents the implementation plan for the Chronic Care Follow-up and Monitoring Program. The initiative is designed to support patients with chronic conditions through follow-up appointments, monitoring forms, secure communication, appointment reminders, and coordinated clinical review. This Week 2 plan converts the Week 1 project strategy into an execution roadmap that identifies the resources, schedule, task dependencies, contingency actions, and change management controls required for a controlled pilot launch.

The implementation is planned across 12 weeks. The first stage focuses on confirming project governance, resource allocation, workflow requirements, and budget readiness. The second stage focuses on platform configuration, privacy checks, patient onboarding materials, and staff preparation. The third stage launches a controlled pilot with selected patients, monitors performance against agreed KPIs, and prepares a scale-up recommendation based on operational evidence.

The plan prioritizes safe implementation rather than rapid launch. Healthcare involves sensitive patient information, clinical workflows, and technology-dependent service delivery. Therefore, the roadmap includes privacy and security review, user testing, staff training, patient education, and contingency plans for technical delays, low adoption, incomplete data, or workflow disruption.

## Project Implementation Snapshot

| Element | Planned Approach |
| --- | --- |
| Project duration | 12 weeks from implementation approval to pilot evaluation |
| Pilot population | Selected chronic care patients requiring follow-up and basic monitoring |
| Core service channels | Video consultation, phone backup, secure patient forms, SMS/email reminders |
| Primary resources | Project manager, clinical lead, doctors/nurses, IT support, admin coordinator, data protection officer |
| Main deliverables | Resource plan, detailed schedule, dependency map, contingency plan, change management process, pilot report |
| Success focus | Safe launch, patient adoption, staff readiness, secure workflows, measurable KPI results |

# 2. Project Context and Implementation Approach

The project continues the Week 1 healthcare initiative and focuses on the execution phase. The proposed service will support chronic care patients who need regular follow-up, medication adherence checks, symptom updates, and basic monitoring of indicators such as blood pressure, glucose readings, and appointment attendance. The implementation plan is structured to reduce operational risk by testing the service with a controlled pilot before wider rollout.

Digital health guidance emphasizes that care should be integrated into real clinical workflows rather than treated as a separate technology add-on. For this reason, the plan links every technical task to a related operational task, such as consent management, clinical escalation, staff training, patient communication, and KPI reporting. Privacy and security are treated as core implementation requirements because telehealth visits, patient messages, and monitoring data involve sensitive health information.

## Implementation Phases

| Phase | Weeks | Purpose | Main Outputs |
| --- | --- | --- | --- |
| Phase 1: Mobilization and resources | 1 to 2 | Confirm governance, team roles, resource needs, and budget release. | Approved implementation plan, resource register, budget allocation |
| Phase 2: Workflow and platform setup | 3 to 5 | Configure the telehealth workflow and patient data collection process. | Configured platform, workflow map, consent process, patient forms |
| Phase 3: Training and readiness | 6 to 8 | Prepare staff, test systems, and finalize launch readiness. | SOPs, training records, test results, launch checklist |
| Phase 4: Pilot launch and monitoring | 9 to 11 | Launch with selected patients and monitor operational performance. | Pilot records, issue log, KPI dashboard updates, improvement actions |
| Phase 5: Evaluation and scale-up decision | 12 | Review results and decide whether the program is ready for expansion. | Final implementation report and scale-up recommendation |

# 3. Implementation Objectives

The implementation objectives translate the project vision into practical execution targets. The objectives are designed to be specific enough for delivery tracking while remaining realistic for a first-stage pilot.

Allocate all human, technical, and financial resources required to launch the pilot within the 12-week implementation window.

Create a detailed schedule that assigns ownership, start and finish points, dependencies, and expected outputs for each major implementation task.

Configure a safe and usable telehealth workflow that includes patient onboarding, consent, consultation, monitoring, follow-up communication, and escalation.

Prepare clinical, administrative, and IT staff through clear SOPs, training sessions, and readiness testing before the pilot launch.

Identify potential implementation delays and prepare contingency actions that reduce disruption to patients, staff, and project outcomes.

Use change management controls to handle new requirements, workflow changes, or unexpected issues during the execution phase.

Track implementation KPIs and use the pilot results to make a scale-up recommendation.

# 4. Resource Identification and Allocation

Resource planning is divided into three categories: human resources, technical resources, and financial resources. The allocation below is based on the project scope from Week 1 and is designed for a realistic pilot rather than a full hospital-wide rollout.

## 4.1 Human Resource Plan

| Role | Core Responsibilities | Allocation | Key Deliverables |
| --- | --- | --- | --- |
| Project Manager | Owns the implementation plan, schedule, risks, budget tracking, issue log, and stakeholder reporting. | 0.5 FTE for 12 weeks | Implementation roadmap, weekly status reports, final pilot report |
| Clinical Lead | Defines clinical workflow, review criteria, escalation process, and care team responsibilities. | 0.25 FTE for 10 weeks | Clinical workflow map, escalation rules, pilot quality review |
| Doctors and Nurses | Deliver follow-up, review monitoring data, document outcomes, and flag patient concerns. | Assigned pilot hours weekly | Consultation notes, monitoring reviews, patient follow-up actions |
| IT Support Officer | Configures platform, user access, reminders, forms, dashboard, and technical support process. | 0.4 FTE for 8 weeks, on-call during pilot | Configured system, UAT report, issue resolution log |
| Data Protection Officer | Reviews consent, privacy notices, access permissions, data retention, and security controls. | Advisory role at key milestones | Privacy review, consent sign-off, risk recommendations |
| Admin Coordinator | Manages scheduling, patient reminders, onboarding calls, documentation, and attendance tracking. | 0.5 FTE for 12 weeks | Appointment tracker, patient onboarding list, communication log |
| Training Coordinator | Prepares staff training materials, schedules sessions, tracks attendance, and collects feedback. | 0.25 FTE for 6 weeks | Training pack, attendance register, staff readiness summary |
| Project Sponsor or Management | Approves budget, major changes, pilot launch, and scale-up decision. | Decision role | Approvals, escalation decisions, scale-up recommendation review |

## 4.2 Technical Resource Plan

| Technical Resource | Purpose | Implementation Notes |
| --- | --- | --- |
| Telehealth platform | Supports secure video consultations and appointment access. | Must be tested for staff login, patient access, waiting room flow, documentation, and phone backup process. |
| Monitoring forms | Collects patient-entered data such as blood pressure, glucose readings, symptoms, and medication adherence. | Forms should be simple, mobile-friendly, and limited to data needed for clinical follow-up. |
| Appointment scheduling tool | Tracks appointments, attendance, cancellations, and follow-up actions. | Should support reminders and weekly attendance reports. |
| Patient communication system | Sends SMS or email reminders, onboarding instructions, and follow-up messages. | Message templates should be approved before patient use. |
| KPI dashboard | Tracks implementation performance and pilot outcomes. | Dashboard should show onboarding, attendance, form completion, issue resolution, satisfaction, and response time. |
| Secure storage and access control | Protects implementation documents, patient forms, and reports. | Access should be role-based and reviewed before launch. |
| IT issue tracker | Records technical incidents, owner, priority, status, and resolution time. | Required during testing and pilot weeks to support timely correction. |

## 4.3 Financial Resource Allocation

The financial resource plan uses the Week 1 preliminary budget and allocates it to implementation activities. The budget is designed for a pilot launch with essential functionality, staff readiness, and basic reporting controls.

| Budget Category | Estimated Cost | Implementation Use | Timing |
| --- | --- | --- | --- |
| Telehealth platform subscription | AED 8,000 | Platform access, video consultation functionality, patient communication support. | Weeks 3 to 12 |
| Monitoring and dashboard setup | AED 5,000 | Monitoring forms, KPI tracking, dashboard configuration, reporting setup. | Weeks 4 to 8 |
| Staff training | AED 4,000 | Training sessions, SOP development, staff readiness support. | Weeks 6 to 8 |
| Patient communication materials | AED 2,000 | Patient guide, onboarding instructions, reminder templates, FAQs. | Weeks 5 to 9 |
| IT support and cybersecurity setup | AED 6,000 | Access controls, testing, issue support, privacy/security configuration. | Weeks 3 to 11 |
| Project management and admin support | AED 7,000 | Planning, scheduling, stakeholder coordination, reporting, pilot administration. | Weeks 1 to 12 |
| Contingency reserve | AED 3,200 | Reserve for delays, extra support, platform adjustments, or additional training. | As needed |
| Total Estimated Budget | AED 35,200 | Total pilot implementation estimate. | Full project |

## 4.4 Resource Allocation by Phase

| Phase | Highest Resource Demand | Reason | Management Action |
| --- | --- | --- | --- |
| Mobilization | Project manager and sponsor | Budget, ownership, and governance must be agreed early. | Confirm decision rights and reporting rhythm. |
| Platform and workflow setup | IT support, clinical lead, data protection officer | Workflow, privacy, and technical setup must be aligned before testing. | Run joint configuration and privacy review sessions. |
| Training and readiness | Training coordinator, clinical staff, admin coordinator | Staff must know how to use the system and follow SOPs before launch. | Track training attendance and collect readiness feedback. |
| Pilot launch | Clinical team, admin coordinator, IT support | Patient usage and technical issues peak during launch. | Provide daily issue review during the first pilot week. |
| Evaluation | Project manager, clinical lead, sponsor | Project decision depends on KPI results and pilot lessons. | Prepare final report with evidence and recommendations. |

# 5. Detailed Task Schedule

The schedule below provides a practical execution plan with owners, timings, dependencies, and outputs. It follows a Gantt-style approach and is designed to support a controlled pilot launch in Week 9 after resources, workflows, training, and testing are completed.

| ID | Task | Start | Finish | Owner | Depends On | Output |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Confirm implementation team and approval path | W1 | W1 | Project Manager | Week 1 project plan | Named implementation team and approval route |
| 1.2 | Finalize resource register and budget allocation | W1 | W2 | Project Manager, Finance | 1.1 | Resource and budget plan |
| 1.3 | Confirm pilot patient profile and eligibility criteria | W2 | W2 | Clinical Lead | 1.1 | Pilot eligibility list |
| 2.1 | Select and configure telehealth platform | W3 | W4 | IT Support | 1.2 | Configured test environment |
| 2.2 | Map patient journey and care workflow | W3 | W4 | Clinical Lead, Admin | 1.3 | Approved workflow map |
| 2.3 | Prepare privacy, consent, and data handling controls | W4 | W5 | Data Protection Officer | 2.1, 2.2 | Consent pack and data access rules |
| 2.4 | Build monitoring forms and KPI dashboard structure | W4 | W6 | IT Support, PM | 2.1, 2.2 | Monitoring forms and KPI template |
| 3.1 | Develop SOPs and training materials | W6 | W6 | Training Coordinator | 2.2, 2.3, 2.4 | SOP and training pack |
| 3.2 | Train clinical, admin, and IT users | W7 | W7 | Training Coordinator | 3.1 | Training completion record |
| 3.3 | Conduct internal testing and user acceptance testing | W8 | W8 | IT Support, Clinical Lead | 3.2 | UAT report and issue log |
| 3.4 | Finalize patient onboarding pack and reminder templates | W7 | W8 | Admin Coordinator | 2.3, 3.1 | Patient guide and message templates |
| 4.1 | Launch pilot with selected patients | W9 | W9 | Project Manager, Clinical Team | 3.3, 3.4 | Pilot launched |
| 4.2 | Monitor attendance, patient forms, issues, and satisfaction | W9 | W11 | PM, Admin, IT | 4.1 | Weekly monitoring reports |
| 4.3 | Adjust workflows and resolve priority issues | W10 | W11 | Project Team | 4.2 | Updated workflow and issue resolutions |
| 5.1 | Evaluate pilot results and prepare scale-up recommendation | W12 | W12 | Project Manager, Sponsor | 4.2, 4.3 | Final implementation report |

# 6. Gantt-Style Implementation Roadmap

The roadmap below shows the planned sequence of work across the 12-week implementation period. Shaded cells indicate active work periods. The schedule is intentionally sequenced so that platform setup, consent, training, and testing are complete before pilot launch.

| Task | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Governance |  |  |  |  |  |  |  |  |  |  |  |  |
| Resource allocation |  |  |  |  |  |  |  |  |  |  |  |  |
| Pilot profile |  |  |  |  |  |  |  |  |  |  |  |  |
| Platform setup |  |  |  |  |  |  |  |  |  |  |  |  |
| Workflow map |  |  |  |  |  |  |  |  |  |  |  |  |
| Privacy controls |  |  |  |  |  |  |  |  |  |  |  |  |
| Forms and dashboard |  |  |  |  |  |  |  |  |  |  |  |  |
| SOPs |  |  |  |  |  |  |  |  |  |  |  |  |
| Staff training |  |  |  |  |  |  |  |  |  |  |  |  |
| Onboarding pack |  |  |  |  |  |  |  |  |  |  |  |  |
| Testing and UAT |  |  |  |  |  |  |  |  |  |  |  |  |
| Pilot launch |  |  |  |  |  |  |  |  |  |  |  |  |
| Pilot monitoring |  |  |  |  |  |  |  |  |  |  |  |  |
| Workflow fixes |  |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |

# 7. Dependency Mapping

Dependency mapping is used to protect the schedule from avoidable sequencing errors. Each dependency below identifies the task that must be completed before another task can begin or be completed safely.

| Task | Depends On | Reason for Dependency | Risk if Ignored |
| --- | --- | --- | --- |
| Telehealth platform configuration | Resource allocation and tool approval | The team cannot configure a system before budget and platform access are confirmed. | Rework, cost variation, or delayed setup |
| Workflow design | Pilot patient profile and clinical scope | The workflow must reflect the type of patients and clinical follow-up required. | Inaccurate patient journey or unclear escalation |
| Consent and privacy controls | Workflow design and platform setup | The privacy review must match the actual data flow and system access model. | Compliance risk and launch delay |
| Monitoring forms and dashboard setup | Workflow design and data requirements | Forms should collect only useful data that supports care review and KPI tracking. | Incomplete, excessive, or unusable data |
| Staff training materials | Final workflow, forms, consent, and platform process | Training must be based on the final process rather than draft assumptions. | Staff confusion and inconsistent use |
| Internal testing and UAT | Platform setup and training completion | Users must test the actual configured system after training. | Technical issues during patient launch |
| Patient onboarding | Consent pack, guide, reminders, and trained admin team | Patients need clear instructions and support before joining the pilot. | Low adoption or missed appointments |
| Pilot launch | System testing, staff training, privacy sign-off, and onboarding materials | The pilot should only launch when service readiness is confirmed. | Patient experience issues and operational disruption |
| Final evaluation | Pilot monitoring and issue resolution data | The scale-up decision must be based on real pilot evidence. | Weak recommendation or unsupported decision |

## Critical Path

The critical path for this pilot is: resource approval, platform configuration, workflow design, privacy and consent sign-off, staff training, internal testing, patient onboarding, pilot launch, monitoring, and final evaluation. Any significant delay in these activities may affect the pilot launch date or the quality of implementation.

## RACI Responsibility Matrix

The RACI matrix clarifies accountability. R = Responsible, A = Accountable, C = Consulted, and I = Informed.

| Activity | PM | Clinical Lead | IT | DPO | Admin | Training | Sponsor |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Resource and budget plan | R/A | C | C | I | C | I | A |
| Workflow design | R | A | C | C | C | I | I |
| Platform configuration | C | C | R/A | C | I | I | I |
| Privacy and consent review | C | C | C | R/A | I | I | I |
| Training materials | C | C | C | I | C | R/A | I |
| Patient onboarding | C | C | I | C | R/A | I | I |
| Pilot launch | A | R | R | C | R | I | I |
| Final evaluation | R/A | C | C | C | C | I | A |

# 8. Contingency Planning

The contingency plan addresses delays and problems that are realistic in a healthcare environment. Each contingency includes a trigger, planned response, owner, and timing impact.

| Potential Issue | Trigger | Impact | Contingency Action | Owner |
| --- | --- | --- | --- | --- |
| Platform approval or configuration delay | Platform not ready by end of Week 4 | Pilot may be delayed | Use an approved temporary video consultation tool and keep monitoring forms separate until full setup is ready. | Project Manager, IT |
| Staff unavailable for training | Less than 90% training attendance by Week 7 | Staff readiness risk | Record training, run catch-up sessions, and provide one-page quick guides before UAT. | Training Coordinator |
| Low patient onboarding completion | Less than 70% of selected patients complete onboarding by Week 9 | Small or biased pilot sample | Add phone support, simplify forms, and send additional reminders through admin team. | Admin Coordinator |
| Technical issues during pilot | More than five unresolved user issues in the first pilot week | Poor patient or staff experience | Assign IT support windows, prioritize high-impact issues, and maintain phone consultation backup. | IT Support |
| Privacy or consent issue identified late | DPO does not approve materials by Week 8 | Compliance risk and possible launch delay | Pause patient onboarding until consent language and data handling steps are corrected. | DPO, PM |
| Incomplete monitoring data | Form completion below 70% during pilot | Weak clinical review and KPI reporting | Shorten the form, add reminder prompts, and ask nurses to review missing data weekly. | Clinical Lead, Admin |
| Budget pressure | Forecast cost exceeds approved budget by more than 10% | Scope reduction may be needed | Use contingency reserve, defer non-essential features, and escalate budget decision to sponsor. | Project Manager, Sponsor |
| Workflow confusion among staff | Repeated errors in appointment documentation or escalation | Operational inconsistency | Hold a short workflow reset session and update the SOP with examples. | Clinical Lead, Training Coordinator |

## Contingency Prioritization Rules

Patient safety, privacy, and service continuity receive the highest priority when resources are limited.

A temporary workaround is acceptable only if it is approved, documented, and does not create unnecessary privacy or clinical risk.

Non-essential reporting features may be delayed, but appointment delivery, consent, access control, and follow-up communication cannot be skipped.

Any contingency that changes scope, budget, or pilot launch date must be reviewed by the project sponsor.

# 9. Change Management Strategy

Healthcare implementation can change quickly because patient needs, staff feedback, platform limitations, privacy guidance, and operational constraints may emerge during testing. The change management strategy below provides a clear process for handling changes without losing control of scope, schedule, budget, or quality.

| Step | Action | Purpose | Output |
| --- | --- | --- | --- |
| 1. Identify change | A team member records a new requirement, problem, or improvement request in the change log. | Ensure no change is handled informally or forgotten. | Change request entry |
| 2. Assess impact | Project manager reviews impact on timeline, budget, risk, privacy, patient experience, and staff workload. | Understand the consequence before taking action. | Impact assessment |
| 3. Categorize priority | Classify the change as urgent, high, medium, or low priority. | Protect patient safety and launch readiness. | Priority rating |
| 4. Approve or reject | Sponsor, clinical lead, or DPO approves changes depending on impact area. | Ensure appropriate decision authority. | Decision record |
| 5. Update project plan | Revise schedule, resource plan, SOP, budget, or dashboard if needed. | Keep documents aligned with reality. | Updated implementation documents |
| 6. Communicate change | Notify affected staff and stakeholders through the agreed channel. | Avoid confusion and inconsistent practice. | Communication note |
| 7. Monitor result | Check whether the change solved the problem and did not create new risks. | Confirm effectiveness. | Follow-up action or closure |

## Change Control Thresholds

| Change Type | Approval Needed | Example |
| --- | --- | --- |
| Minor operational change | Project Manager | Adjust reminder wording or meeting frequency. |
| Clinical workflow change | Clinical Lead and Project Manager | Add an escalation step for abnormal patient readings. |
| Privacy or data change | Data Protection Officer | Collect an additional data field or change data storage location. |
| Budget change | Project Sponsor | Use contingency reserve or request extra IT support budget. |
| Schedule change affecting pilot launch | Project Sponsor and Project Manager | Move pilot launch by one week due to platform delay. |
| Scope expansion | Project Sponsor | Add a second patient group or new monitoring device requirement. |

## Change Management Communication Principles

Explain the reason for the change in practical terms rather than only using project terminology.

Tell staff exactly what is changing, when it changes, and what they need to do differently.

Avoid introducing multiple changes at once during the pilot unless patient safety or privacy requires it.

Keep a simple change log so the final evaluation can explain which adjustments improved the pilot.

# 10. Communication and Reporting Plan

A structured communication plan supports timely decision-making and prevents implementation gaps. The plan below matches each audience with the information they need, the communication method, and the expected frequency.

| Audience | Information Shared | Method | Frequency | Owner |
| --- | --- | --- | --- | --- |
| Project team | Task progress, risks, dependencies, issues, and next actions. | Weekly implementation meeting and action tracker. | Weekly | Project Manager |
| Project sponsor/management | Progress summary, budget status, key risks, launch readiness, and decisions needed. | Two-weekly status report. | Every 2 weeks | Project Manager |
| Clinical staff | Workflow updates, training reminders, escalation process, patient follow-up notes. | Training sessions, SOP updates, staff briefings. | As needed and before launch | Clinical Lead |
| Admin team | Appointment scheduling rules, reminder process, onboarding list, attendance tracking. | Checklists, shared tracker, short briefings. | Weekly during setup and pilot | Admin Coordinator |
| IT team | Configuration tasks, test issues, access requests, dashboard changes, support tickets. | Issue tracker and technical stand-up. | Weekly, then daily in pilot launch week | IT Support Officer |
| Patients | Onboarding steps, consent information, appointment reminders, how to submit forms, support contact. | SMS/email reminders, patient guide, support calls. | Before and during pilot | Admin Coordinator |
| Data protection officer | Privacy changes, consent forms, access controls, data handling process. | Review meetings and document sign-off. | At key milestones | Project Manager |

## Weekly Status Report Format

The project manager should use a short weekly status report with the following fields: completed activities, planned activities, risks/issues, decisions needed, budget notes, change requests, and launch readiness status. During pilot weeks, the report should also include patient attendance, monitoring form completion, satisfaction feedback, and technical issue resolution time.

# 11. Implementation KPIs

The implementation KPIs are designed to measure whether the project is ready to launch and whether the pilot is operating effectively. These indicators should be reviewed weekly during implementation and in detail at the final evaluation stage.

| KPI | Target | Measurement Method | Review Timing |
| --- | --- | --- | --- |
| Resource allocation completion | 100% of named roles assigned by Week 2 | Resource register review | Week 2 |
| Platform configuration completion | 100% of core platform functions configured by Week 4 | IT setup checklist | Week 4 |
| Privacy and consent sign-off | Approved before patient onboarding begins | DPO sign-off record | Week 5 to 8 |
| Staff training completion | 100% of required staff trained before pilot launch | Training attendance register | Week 7 |
| Internal testing completion | 100% of critical test cases passed before pilot launch | UAT test report | Week 8 |
| Patient onboarding completion | 85% or higher | Onboarding tracker | Week 9 |
| Appointment attendance rate | 80% or higher | Scheduling report | Weeks 9 to 11 |
| Monitoring form completion | 80% or higher | Form submission tracker | Weeks 9 to 11 |
| Average technical issue resolution time | Within 24 hours for priority issues | Issue tracker | Weeks 8 to 11 |
| Patient satisfaction score | 4 out of 5 or higher | Short patient feedback form | Weeks 10 to 12 |
| Pilot completion rate | 90% of selected patients complete the pilot pathway | Pilot participation report | Week 12 |

# 12. Final Deliverables and Acceptance Criteria

The Week 2 implementation plan should produce practical deliverables that can be used during the execution phase. Each deliverable has an acceptance criterion to make completion clear and measurable.

| Deliverable | Description | Acceptance Criteria |
| --- | --- | --- |
| Resource allocation plan | List of required human, technical, and financial resources. | All key roles, systems, and budget categories are identified with owners. |
| Detailed task schedule | Implementation task list with start dates, finish dates, dependencies, and owners. | All major tasks are sequenced from Week 1 to Week 12. |
| Gantt-style roadmap | Visual schedule showing active weeks for each task. | Roadmap clearly shows launch preparation, pilot launch, monitoring, and evaluation. |
| Dependency map | Summary of task relationships and sequencing logic. | Critical dependencies and launch blockers are clearly explained. |
| RACI matrix | Responsibility chart for implementation activities. | Accountable and responsible roles are defined for major activities. |
| Contingency plan | Backup actions for technical, staffing, adoption, privacy, and budget risks. | Each major issue has a trigger, response, and owner. |
| Change management process | Controlled method for assessing, approving, and communicating changes. | Approval thresholds and change steps are documented. |
| Communication plan | Stakeholder communication channels, frequency, and owner. | All key internal and patient-facing communication needs are included. |
| Implementation KPI plan | Targets and measurement methods for readiness and pilot performance. | KPIs include resource readiness, training, testing, onboarding, attendance, satisfaction, and issue resolution. |
| Final implementation report | Pilot results, lessons learned, issues, and scale-up recommendation. | Report is completed in Week 12 using KPI evidence and stakeholder feedback. |

## Launch Readiness Checklist

| Readiness Item | Required Before Pilot Launch |
| --- | --- |
| Project sponsor approval | Yes |
| Telehealth platform configured and tested | Yes |
| Privacy and consent materials approved | Yes |
| Staff training completed | Yes |
| Patient onboarding guide ready | Yes |
| Reminder templates approved | Yes |
| IT issue support process active | Yes |
| KPI dashboard or tracker ready | Yes |
| Phone backup process defined | Yes |
| Pilot patient list confirmed | Yes |

# 13. Conclusion

This Week 2 implementation plan provides a practical execution roadmap for the Chronic Care Follow-up and Monitoring Program. It identifies the required resources, assigns responsibilities, schedules the work across 12 weeks, maps key dependencies, and establishes controls for contingency planning and change management. The plan supports a safe and realistic pilot launch by ensuring that technology, people, workflows, privacy controls, and patient communication materials are ready before patients begin using the service.

The most important implementation priorities are platform readiness, clinical workflow clarity, patient consent, staff training, patient onboarding, and issue response during the pilot. If these areas are managed carefully, the project team will be able to evaluate the pilot using meaningful evidence and decide whether the healthcare service should be expanded.

# 14. References

World Health Organization. (2021). Global strategy on digital health 2020-2025. https://www.who.int/publications/i/item/9789240020924

American Medical Association. (n.d.). Telehealth Implementation Playbook. https://www.ama-assn.org/system/files/ama-telehealth-playbook.pdf

U.S. Department of Health and Human Services. (2024). Privacy and security for telehealth. https://telehealth.hhs.gov/providers/best-practice-guides/privacy-and-security-telehealth

U.S. Department of Health and Human Services, Office for Civil Rights. (2023). Telehealth privacy and security tips for patients. https://www.hhs.gov/hipaa/for-professionals/privacy/guidance/telehealth-privacy-security/index.html

Project Management Institute. (2021). A guide to the Project Management Body of Knowledge, Seventh Edition. Project Management Institute.