Week 1 Task

Project Planning and Strategy

Chronic Care Follow-up and Monitoring Program

| Prepared by | Shaghayegh Haghbin |
| --- | --- |
| Project type | Healthcare initiative |
| Planning horizon | 12-week pilot implementation |
| Location context | Dubai, UAE healthcare operations setting |
| Submission format | Professional project plan document |

Document purpose

This document presents a complete project plan for a healthcare initiative, including objectives, scope, stakeholders, work breakdown structure, timeline, budget estimate, risks, KPIs, deliverables, and implementation governance.

# 1. Executive Summary

This project plan proposes a Chronic Care Follow-up and Monitoring Program for patients who require ongoing support for conditions such as diabetes, hypertension, cardiovascular risk, or post-discharge follow-up. The initiative will provide scheduled consultations, patient onboarding, digital reminders, health data collection, care coordination, and simple KPI reporting. The program is designed as a 12-week pilot that can be scaled after operational testing.

The plan focuses on practical healthcare operations rather than advanced clinical diagnosis. It aims to improve access, reduce missed follow-up appointments, strengthen patient communication, and provide healthcare teams with organized monitoring data. The project also recognizes that healthcare requires strong planning around privacy, cybersecurity, patient consent, staff training, and workflow integration.

## Project Snapshot

| Item | Plan |
| --- | --- |
| Project name | Chronic Care Follow-up and Monitoring Program |
| Pilot duration | 12 weeks |
| Target users | Adult chronic care patients requiring routine follow-up |
| Service model | Teleconsultations, digital reminders, monitoring forms, and care coordination |
| Primary outcome | Improved follow-up completion and patient communication |
| Estimated budget | AED 35,200 |
| High-priority risks | Privacy, cybersecurity, patient adoption, staff readiness, technical downtime |

# 2. Project Background and Context

Digital health is increasingly used to support healthcare delivery through telemedicine, electronic health records, patient portals, patient monitoring, digital therapeutics, and artificial intelligence. The World Health Organization describes digital health as a route to support healthy lives and wellbeing, while the OECD highlights the role of high-quality and interoperable health data in making digital health systems efficient, resilient, and equitable [1][2].

Healthcare is especially useful for chronic care because patients often require regular follow-ups, education, medication adherence checks, and symptom monitoring rather than emergency intervention. A structured program can help reduce missed follow-ups, improve continuity of care, and give clinical teams more organized patient information before each appointment.

However, healthcare projects also create operational risks. The AMA Telehealth Implementation Playbook highlights important implementation considerations such as workflow design, licensing, consent, privacy, and security [3]. Healthcare cybersecurity is also a major planning issue because digital healthcare services depend on patient trust, secure access, and reliable systems [4].

## Key Issues This Project Addresses

Patients may miss routine follow-ups because of scheduling barriers, travel time, or limited reminder systems.

Healthcare staff may not have a consistent process for collecting home readings or patient-reported symptoms.

Care coordination can become fragmented when appointment, communication, and monitoring data are stored separately.

Care can create privacy, security, and documentation risks if it is implemented without clear controls.

Patients and staff may need simple training to confidently use care tools.

## Proposed Solution

The project will establish a controlled care pilot using a secure telehealth platform, standardized onboarding materials, consent forms, weekly monitoring forms, reminder workflows, staff training, a risk register, and a KPI dashboard. The pilot will start with a manageable patient group, evaluate performance, resolve issues, and produce a recommendation for scale-up.

# 3. Project Objectives and Success Criteria

The project objectives are designed to be specific, measurable, achievable, relevant, and time-bound. They focus on operational delivery, patient experience, and safe implementation.

| No. | Objective | Success Criteria |
| --- | --- | --- |
| 1 | Launch a chronic care follow-up pilot within 12 weeks. | Pilot goes live by Week 9 and completes evaluation by Week 12. |
| 2 | Improve appointment coordination and reduce missed follow-ups. | Reduce missed follow-up rate by at least 20% compared with the baseline pilot group. |
| 3 | Collect basic monitoring information in a structured format. | At least 80% of pilot patients submit monitoring forms on schedule. |
| 4 | Improve patient communication and access to follow-up support. | Average response time to routine patient queries is under 24 hours. |
| 5 | Prepare staff to manage the workflow confidently. | 100% of assigned staff complete training and sign off on SOPs. |
| 6 | Protect patient information and clinical documentation. | Privacy controls, user access rules, consent, and escalation procedures are approved before launch. |

## Expected Benefits

Better continuity of care for patients with chronic conditions.

Fewer missed appointments through digital reminders and follow-up calls.

More organized patient information before consultations.

Clearer roles for doctors, nurses, admin staff, and IT support.

A scalable operating model that can be expanded after the pilot.

# 4. Scope Statement

The scope defines what the project will and will not deliver during the 12-week pilot. This prevents scope creep and ensures the project remains realistic for a Week 1 planning submission.

| Scope Area | Description |
| --- | --- |
| In scope | Consultation workflow, patient onboarding, consent process, appointment reminders, monitoring forms, staff training, SOPs, basic dashboard reporting, risk management, pilot evaluation. |
| Out of scope | Emergency medical care, in-person treatment, medical diagnosis without clinician review, replacement of a hospital electronic medical record, advanced AI diagnosis, full integration with all external systems. |
| Target patient group | Adult chronic care patients who require routine follow-up and are clinically suitable for care. |
| Pilot size assumption | 30 to 50 patients for the initial pilot, depending on staff capacity and clinical approval. |
| Primary service channels | Secure telehealth platform, phone backup, SMS or email reminders, online forms, and internal dashboard. |

## Project Boundaries

The program supports routine follow-up only. Emergency symptoms will be escalated to emergency care or urgent clinical pathways.

Clinical decisions remain with licensed healthcare professionals. The project team manages operational design, not diagnosis.

Only necessary patient data will be collected for the pilot, and access will be limited to authorized staff.

The pilot will use a basic KPI dashboard. Complex analytics and AI prediction are reserved for future phases.

# 5. Stakeholder Analysis

Stakeholder management is essential because healthcare affects patients, clinical teams, operational teams, IT support, and leadership. Each group needs clear responsibilities and communication.

| Stakeholder | Role | Influence | Engagement Need |
| --- | --- | --- | --- |
| Patients | Use the service, attend appointments, submit readings, provide feedback. | High | Simple onboarding, reminders, support contact, privacy explanation. |
| Doctors | Conduct consultations, review patient data, make clinical decisions. | High | Workflow briefing, clinical escalation process, structured visit notes. |
| Nurses or Care Coordinators | Review submissions, follow up with patients, escalate concerns. | High | Training, daily task list, escalation criteria, dashboard access. |
| Admin and Operations Team | Schedule appointments, send reminders, track attendance, update logs. | High | Scheduling SOP, reminder templates, weekly reporting cadence. |
| IT Support | Configure platform, manage access, troubleshoot issues, support cybersecurity. | High | Technical checklist, user access matrix, incident response procedure. |
| Data Protection or Compliance Lead | Review consent, privacy rules, data handling, documentation. | High | Privacy checklist, approval gate before pilot launch. |
| Project Manager | Manage plan, timeline, risks, meetings, reporting, and delivery. | High | Weekly project updates, risk register, issue tracker. |
| Senior Management | Approve budget, monitor outcomes, decide scale-up. | Medium | Milestone reports and final pilot evaluation. |

## RACI Summary

| Activity | Responsible | Accountable | Consulted | Informed |
| --- | --- | --- | --- | --- |
| Project charter approval | Project Manager | Senior Management | Clinical Lead | All project team |
| Clinical workflow design | Clinical Lead | Senior Management | Doctors, Nurses, Compliance | Admin, IT |
| Platform configuration | IT Support | Project Manager | Compliance, Clinical Lead | Users |
| Patient onboarding | Care Coordinator | Clinical Lead | Admin, Compliance | Patients |
| Training delivery | Project Manager | Clinical Lead | IT, Compliance | All assigned staff |
| KPI reporting | Project Manager | Senior Management | Admin, Clinical Lead | Project team |

# 6. Work Breakdown Structure (WBS)

The WBS breaks the project into manageable work packages. It supports scheduling, responsibility assignment, milestone tracking, and risk control.

| WBS | Work Package | Activities | Output | Timing |
| --- | --- | --- | --- | --- |
| 1.0 | Initiation and Approval | Define project charter, objectives, assumptions, budget range, and governance. | Approved charter and sponsor sign-off | Week 1 |
| 2.0 | Research and Requirements | Review care trends, patient journey, staff needs, privacy requirements, and baseline process. | Requirements document | Week 2 |
| 3.0 | Workflow and SOP Design | Map appointment process, monitoring workflow, escalation rules, reminders, and documentation steps. | Approved SOPs and workflow map | Weeks 3-4 |
| 4.0 | Platform and Data Setup | Configure telehealth platform, forms, user roles, dashboard fields, access controls, and test environment. | Configured pilot tools | Weeks 5-6 |
| 5.0 | Training and Change Management | Prepare training materials, run staff sessions, collect sign-off, and answer user questions. | Training completion log | Weeks 6-7 |
| 6.0 | Patient Onboarding | Create patient guide, consent process, eligibility list, onboarding calls, and reminder templates. | Onboarded pilot patients | Weeks 7-8 |
| 7.0 | Testing and Readiness | Conduct internal tests, privacy review, technical checks, scenario testing, and launch readiness meeting. | Go-live checklist | Week 8 |
| 8.0 | Pilot Launch | Start appointments, monitor submissions, manage issues, and track daily operations. | Operational pilot | Week 9 |
| 9.0 | Monitoring and Reporting | Track KPIs, patient feedback, staff issues, data completeness, and appointment performance. | Weekly dashboard and issue log | Weeks 9-11 |
| 10.0 | Evaluation and Scale-up Plan | Evaluate pilot, document lessons learned, update risks, and recommend scale-up decision. | Final evaluation report | Week 12 |

## Dependencies

Platform configuration depends on approval of requirements and privacy controls.

Patient onboarding depends on approved consent wording and clinical eligibility criteria.

Pilot launch depends on staff training completion, technical testing, and go-live approval.

Final evaluation depends on complete KPI tracking and feedback collection during the pilot.

# 7. Timeline and Milestones

The implementation timeline is designed as a 12-week pilot. The timeline allows enough time for requirements gathering, workflow design, platform setup, training, testing, pilot operation, and final evaluation.

| Week | Main Activity | Milestone |
| --- | --- | --- |
| Week 1 | Project initiation, objectives, stakeholders, sponsor approval | Project charter approved |
| Week 2 | Research, baseline process review, patient journey mapping | Requirements confirmed |
| Week 3 | Workflow design, roles, appointment process, monitoring process | Draft workflow map |
| Week 4 | Risk planning, budget finalization, SOP review | Budget and risk register approved |
| Week 5 | Telehealth platform configuration and user access setup | System configuration started |
| Week 6 | Monitoring forms, dashboard fields, cybersecurity checks | Pilot tool setup completed |
| Week 7 | Staff training materials, SOP training, patient guide development | Training package completed |
| Week 8 | Internal testing, consent review, readiness assessment | Go-live approval |
| Week 9 | Pilot launch with selected patients | Pilot live |
| Week 10 | Monitor appointments, patient submissions, issues, and feedback | Weekly KPI report 1 |
| Week 11 | Resolve issues, improve reminders, update SOPs | Improvement log completed |
| Week 12 | Final evaluation, lessons learned, scale-up recommendation | Final pilot report submitted |

## Milestone Summary

| Milestone | Description | Target Date |
| --- | --- | --- |
| M1 | Project charter approved | End of Week 1 |
| M2 | Requirements and scope approved | End of Week 2 |
| M3 | Workflow, SOPs, risk register, and budget approved | End of Week 4 |
| M4 | Platform and monitoring forms configured | End of Week 6 |
| M5 | Staff training and patient materials completed | End of Week 7 |
| M6 | Pilot readiness approved | End of Week 8 |
| M7 | Pilot launched | Week 9 |
| M8 | Final evaluation submitted | End of Week 12 |

# 8. Resource Plan and Estimated Budget

The budget is a preliminary estimate for a small 12-week pilot. Actual costs may vary depending on the selected platform, internal staff availability, data protection requirements, and number of patients.

| Budget Item | Purpose | Estimated Cost (AED) |
| --- | --- | --- |
| Telehealth platform subscription or pilot license | Secure consultation capability, basic patient communication, admin access | 8,000 |
| Monitoring forms and dashboard setup | Patient readings, symptom check forms, status dashboard, simple reporting | 5,000 |
| Staff training | Training sessions for doctors, nurses, admin staff, and IT support | 4,000 |
| Patient communication materials | Patient guide, onboarding script, consent explainer, reminder templates | 2,000 |
| IT support and cybersecurity setup | Access controls, testing, troubleshooting, privacy settings, support coverage | 6,000 |
| Project management and admin support | Planning, coordination, reporting, issue tracking, meeting documentation | 7,000 |
| Contingency reserve, 10% | Buffer for platform changes, support needs, minor implementation delays | 3,200 |
| Total estimated budget | Preliminary pilot budget | 35,200 |

## Resource Requirements

| Resource | Estimated Allocation | Responsibility |
| --- | --- | --- |
| Project Manager | Part-time | Owns plan, timeline, risks, stakeholder coordination, and reporting. |
| Clinical Lead | Part-time | Approves clinical workflow, eligibility criteria, escalation rules, and SOPs. |
| Doctors | Allocated clinic sessions | Conduct consultations and clinical review. |
| Nurses or Care Coordinators | Part-time | Review submissions, follow up with patients, and escalate concerns. |
| Admin Coordinator | Part-time | Schedules appointments, sends reminders, and updates attendance logs. |
| IT Support | Part-time | Configures platform, resolves issues, manages access, and checks security. |
| Compliance or Data Protection Lead | Review role | Checks consent, privacy, documentation, and data handling controls. |

# 9. Risk Analysis and Contingency Plan

Risk management is a critical part of the project because healthcare involves patient data, communication, clinical workflow changes, and technical reliability. The following risk register identifies likely project risks and mitigation actions.

| Risk | Impact | Likelihood | Priority | Mitigation and Contingency |
| --- | --- | --- | --- | --- |
| Patient data breach or unauthorized access | High | Medium | High | Use approved platform, role-based access, strong passwords, staff training, privacy checklist, audit trail. |
| Low patient adoption | Medium | Medium | Medium | Provide simple onboarding guide, phone support, reminder calls, and clear benefits explanation. |
| Staff resistance or low confidence | Medium | Medium | Medium | Involve staff early, provide practical training, create quick reference guides, collect feedback. |
| Technical downtime during appointments | High | Medium | High | Run pre-launch testing, assign IT support, maintain phone call backup, document issue resolution process. |
| Missed appointments | Medium | High | Medium | Use SMS or email reminders, day-before confirmation, and follow-up call process. |
| Incomplete monitoring data | Medium | Medium | Medium | Simplify forms, send reminders, review dashboard weekly, follow up with patients who miss submissions. |
| Privacy or consent gaps | High | Low | High | Review consent wording, store documentation, train staff, include privacy approval before go-live. |
| Clinical escalation delay | High | Low | High | Define escalation criteria, assign clinical owner, use daily review process for flagged submissions. |
| Budget overrun | Medium | Medium | Medium | Use phased rollout, maintain 10% contingency, approve additional spending through project sponsor. |
| Scope creep | Medium | Medium | Medium | Use scope statement, change request log, sponsor approval for major changes. |

## Risk Response Approach

High-priority risks will be reviewed every week during the pilot planning and launch stages.

Any privacy, cybersecurity, or clinical escalation risk must be resolved before go-live approval.

The project manager will maintain an issue log that records the owner, due date, status, and resolution.

Technical incidents during patient care will use the phone backup workflow and will be documented for root cause review.

# 10. Communication and Governance Plan

The communication plan keeps stakeholders aligned and ensures issues are escalated quickly. Clear communication is important because healthcare projects require coordination across clinical, operational, IT, and compliance teams.

| Communication | Audience | Content | Frequency | Owner |
| --- | --- | --- | --- | --- |
| Weekly project meeting | Project team | Project status, risks, decisions, action items | Weekly | Project Manager |
| Clinical workflow review | Clinical Lead, doctors, nurses | Clinical process, escalation rules, patient eligibility | Weeks 2-4 and as needed | Clinical Lead |
| IT readiness check | IT, Project Manager, Compliance | Platform setup, access controls, testing, issue log | Weeks 5-8 | IT Support |
| Pilot performance update | Senior Management | KPIs, risks, budget, pilot issues | Weeks 9-12 | Project Manager |
| Patient communications | Pilot patients | Appointment reminders, onboarding instructions, support information | As scheduled | Admin Coordinator |
| Final review meeting | Senior Management and project team | Pilot results, lessons learned, scale-up decision | Week 12 | Project Manager |

## Governance Model

| Governance Role | Decision Responsibility |
| --- | --- |
| Project Sponsor | Approves budget, major decisions, scope changes, and scale-up recommendation. |
| Project Manager | Controls plan, risk register, timeline, project reporting, and team coordination. |
| Clinical Lead | Approves clinical workflow, patient eligibility, safety escalation, and care quality. |
| Compliance Lead | Approves data handling, privacy statements, consent process, and documentation. |
| IT Lead | Approves technical readiness, access controls, testing, and support coverage. |

# 11. Key Performance Indicators (KPIs)

KPIs will measure whether the pilot is operationally successful, safe, and acceptable to patients and staff. The dashboard should be reviewed weekly during the pilot launch period.

| KPI | Definition | Target | Review Cycle |
| --- | --- | --- | --- |
| Patient onboarding completion rate | Percentage of selected patients who complete onboarding and consent | 85% or higher | Weekly |
| Missed appointment reduction | Change in missed follow-ups compared with baseline | 20% reduction | End of pilot |
| Monitoring form completion | Percentage of expected forms submitted by patients | 80% or higher | Weekly |
| Average response time to patient queries | Time from routine query received to response sent | Under 24 hours | Weekly |
| Patient satisfaction score | Average score from post-pilot survey | 4.0 out of 5 or higher | End of pilot |
| Staff training completion | Assigned staff who complete training and SOP sign-off | 100% | Before go-live |
| Platform uptime | Availability of platform during scheduled service hours | 95% or higher | Weekly |
| Issue resolution rate | Percentage of logged issues closed by target date | 90% or higher | Weekly |
| Pilot completion rate | Patients who remain active until pilot end | 90% of onboarded patients | End of pilot |

## Dashboard Fields

Patient onboarding status and consent status.

Appointment scheduled, completed, missed, or rescheduled.

Monitoring form submitted or missing.

Flagged symptoms or readings requiring clinical review.

Patient query response time.

Technical issue count, type, owner, and status.

# 12. Deliverables and Acceptance Criteria

The project deliverables convert planning work into clear outputs that can be reviewed and approved. Each deliverable has basic acceptance criteria to confirm completion.

| Deliverable | Acceptance Criteria |
| --- | --- |
| Project charter | Objectives, scope, sponsor, assumptions, timeline, and budget summary are documented and approved. |
| Stakeholder register | Key stakeholders, roles, influence, and engagement needs are identified. |
| Workflow map and SOPs | Appointment, monitoring, escalation, reminder, and documentation workflows are approved. |
| WBS and timeline | Tasks, dependencies, milestones, and 12-week timeline are clearly documented. |
| Budget estimate | Preliminary cost categories and contingency are included. |
| Risk register | Risks include impact, likelihood, priority, mitigation, contingency, and owner. |
| Patient onboarding guide | Guide explains service, consent, appointment process, data submission, and support contact. |
| Staff training plan | Training materials, attendance log, SOP sign-off, and support process are ready. |
| KPI dashboard plan | KPI definitions, targets, review cycle, and dashboard fields are documented. |
| Final pilot evaluation report | Summarizes KPIs, risks, issues, lessons learned, and scale-up recommendation. |

## Quality Standards

All patient-facing materials must use clear and simple language.

All staff workflows must identify the process owner and escalation path.

All patient data must be collected only when necessary for the pilot objective.

All pilot reports must use aggregated data where possible to reduce privacy risk.

All changes after approval must be documented in the project issue or change log.

# 13. Implementation Assumptions and Constraints

| Type | Statement |
| --- | --- |
| Assumptions | The organization already has access to basic internet connectivity, staff email, patient communication channels, and management support for a small pilot. |
| Assumptions | Patients selected for the pilot are clinically appropriate for follow-up and are not relying on this service for emergencies. |
| Assumptions | Internal staff are available part-time to support planning, training, and pilot operations. |
| Constraints | Budget is limited to a small pilot and does not include full enterprise system integration. |
| Constraints | The project timeline is 12 weeks, so the first phase will prioritize a controlled pilot over a full launch. |
| Constraints | The project must follow organizational privacy, security, and clinical governance requirements before launch. |

## Change Control

Any change that affects the approved scope, budget, timeline, privacy controls, or clinical workflow must be reviewed by the Project Manager and approved by the relevant sponsor or lead. Minor changes can be recorded in the issue log, while major changes require formal approval.

# 14. Conclusion

The Chronic Care Follow-up and Monitoring Program provides a realistic and structured plan for launching a small healthcare pilot. It aligns with project management principles by defining clear objectives, scope, WBS, stakeholders, timeline, budget, risks, communication needs, KPIs, deliverables, assumptions, and acceptance criteria.

The strongest feature of this plan is its focus on operational readiness and risk management. The project does not assume that technology alone will improve healthcare delivery. Instead, it combines workflow design, patient onboarding, staff training, privacy controls, technical readiness, and KPI monitoring. This approach makes the project feasible, safe, and suitable for gradual scale-up after the 12-week pilot.

# 15. References

[1] World Health Organization. Global Strategy on Digital Health 2020-2025. https://www.who.int/publications/i/item/9789240020924

[2] OECD. Digital Health and Health at a Glance 2025: Data and Digital. https://www.oecd.org/en/topics/policy-issues/digital-health.html

[3] American Medical Association. Telehealth Implementation Playbook. https://www.ama-assn.org/system/files/ama-telehealth-playbook.pdf

[4] HIMSS. Healthcare Cybersecurity and Digital Health Transformation resources. https://www.himss.org/resources/himss-healthcare-cybersecurity-survey/

# 16. Submission Checklist

| Requirement | Included |
| --- | --- |
| Project objectives included | Yes |
| Scope statement included | Yes |
| Stakeholders included | Yes |
| WBS included | Yes |
| Timeline and milestones included | Yes |
| Estimated budget included | Yes |
| Risk analysis included | Yes |
| KPIs included | Yes |
| Deliverables included | Yes |
| References included | Yes |